## Wks 15 - 16
Report covers outages commencing/returning/spanning the period: 11/04/2022 - 24/04/2022
Outages commencing/returning in Week 15
OUTAGE ID | PLANT |  | Week 15 | [6 empty] | Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-22-110 kV A1 @ CSH-06 | CASHLA 110 kV A1 | bar: Week 15 Mo 11 to Week 15 Th 14
TO-22-110 kV B1 @ CSH-06 | CASHLA 110 kV B1 | bar: Week 15 Mo 11 to Week 15 Th 14
TO-22-CSH-CAP1-01 | CASHLA CAP1 | bar: Week 15 Mo 11 to Week 15 Th 14
TO-22-CNO-KPG-1-01 | COOLNANOONAGH KILPADDOGE | bar: Week 15 Mo 11 to Week 15 Th 14
TO-22-CNO-T131-01 | COOLNANOONAGH T131 | bar: Week 15 Mo 11 to Week 15 Th 14
TO-22-TB-T102-01 | TARBERT T102 | bar: Week 15 Mo 11 to Week 15 Th 14
TO-22-GRI-T141-01 | GRIFFINRATH T141 | bar: Week 15 Mo 11 to Week 16 Tu 19
TO-22-GRI,T-GCA-1-01 | GRIFFINRATH tee GRANGE CASTLE | bar: Week 15 Mo 11 to Week 16 Tu 19
TO-22-GRI,T-GRI-1-01 | GRIFFINRATH tee GRIFFINRATH | bar: Week 15 Mo 11 to Week 16 Tu 19
TO-22-GRI,T-MAY-1-01 | GRIFFINRATH tee MAYNOOTH | bar: Week 15 Mo 11 to Week 16 Tu 19
TO-22-KNY-SAL-1-03 | KNOCKRANNY SALTHILL | bar: Week 15 Mo 11 to Week 16 Tu 19
TO-22-LET-SVC-01 | LETTERKENNY SVC | bar: Week 15 Mo 11 to Week 16 Tu 19
TO-22-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Su 10 to Week 15 Mo 11
TO-22-BLC-DND-1-01 | BELCAMP DARNDALE 1 | bar: Week 15 Tu 12
TO-22-CUN-GLR-1-01 | CUNGHILL GLENREE | bar: Week 15 Tu 12
TO-22-DGN-WOH-1-01 | DUNGARVAN WOODHOUSE | bar: Week 15 Tu 12 to Week 15 Th 14
TO-22-KIN-110SA1-2CB-04 | KINNEGAD 110SA1-2CB | bar: Week 15 Tu 12 to Week 15 Th 14
TO-22-CHA-GLE-1-01 | CHARLEVILLE GLENLARA | bar: Su 10 to Week 15 Tu 12
TO-22-220 kV A2 @ CDU-02 | CORDUFF 220 kV A2 | bar: Su 10 to Week 15 Tu 12
TO-22-220 kV B2 @ CDU-06 | CORDUFF 220 kV B2 | bar: Su 10 to Week 15 Tu 12
TO-22-BLC-DND-3-01 | BELCAMP DARNDALE 3 | bar: Week 15 We 13
TO-22-110 kV A1/A2 @ CLG-01 | CLOGHRAN 110 kV A1/A2 | bar: Week 15 We 13
TO-22-110 kV B1/B2 @ CLG-01 | CLOGHRAN 110 kV B1/B2 | bar: Week 15 We 13
TO-22-DND-110K1-01 | DARNDALE 110K1 | bar: Week 15 We 13
TO-22-DND-110K2-01 | DARNDALE 110K2 | bar: Week 15 We 13
TO-22-GOR-NAV-2-01 | GORMAN NAVAN 2 | bar: Week 15 We 13
TO-22-BOL-ENN-1-01 | BOOLTIAGH ENNIS | bar: Week 15 We 13 to Week 15 Th 14
TO-22-KPG-TRL-1-02 | KILPADDOGE TRALEE 1 | bar: Su 10 to Week 15 We 13
TO-22-400 kV A1 @ WOO-02 | WOODLAND 400 kV A1 | bar: Su 10 to Week 15 We 13
TO-22-400 kV A2 @ WOO-01 | WOODLAND 400 kV A2 | bar: Su 10 to Week 15 We 13
TO-22-400 kV B1 @ WOO-02 | WOODLAND 400 kV B1 | bar: Su 10 to Week 15 We 13
TO-22-400 kV B2 @ WOO-01 | WOODLAND 400 kV B2 | bar: Su 10 to Week 15 We 13
TO-22-WOO-400K1-2-02 | WOODLAND 400K1-2 | bar: Su 10 to Week 15 We 13
TO-22-BRT-220K2-01 | BRACETOWN 220K2 | bar: Week 15 Th 14
TO-22-BDA-MON-1-01 | BARODA MONREAD | bar: Su 10 to Week 15 Th 14
TO-22-110 kV B2 @ DEY-02 | DERRYCARNEY 110 kV B2 | bar: Su 10 to Week 15 Th 14
TO-22-DEY-110K2-01 | DERRYCARNEY 110K2 | bar: Su 10 to Week 15 Th 14
TO-22-MON-110SA1-01 | MONREAD 110SA1 | bar: Su 10 to Week 15 Th 14
TO-22-MON-110SA2-02 | MONREAD 110SA2 | bar: Su 10 to Week 15 Th 14
TO-22-MON-T101-01 | MONREAD T101 | bar: Su 10 to Week 15 Th 14
TO-22-CLA-CKN-1-01 | CLASHAVOON CLONKEEN | bar: Su 10 to Week 15 Fr 15
Outages commencing/returning in Week 16
OUTAGE ID | PLANT | Week 15 Mo 11: Week 15; Week 16 Mo 18: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-22-CBT-220K1-01 | CASTLEBAGOT 220K1 | bar: Week 16 Tu 19
TO-22-KPG-TB-2-03 | KILPADDOGE TARBERT 2 | bar: Week 16 Tu 19
TO-22-WEX-110SA1-2CB-01 | WEXFORD 110SA1-2CB | bar: Week 16 Tu 19
TO-22-WEX-T141-01 | WEXFORD T141 | bar: Week 16 Tu 19
TO-22-BK-110SA1-03 | BELLACORICK 110SA1 | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-BK-110SA2-02 | BELLACORICK 110SA2 | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-BK-SKY-1-02 | BELLACORICK SRAHNAKILLY | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-BK-T122-01 | BELLACORICK T122 | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-110 kV A1 @ FLA-02 | FLAGFORD 110 kV A1 | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-110 kV B1 @ FLA-02 | FLAGFORD 110 kV B1 | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-SKY-T131-03 | SRAHNAKILLY T131 | bar: Week 16 Tu 19 to Week 16 We 20
TO-22-CLA-KRA-1-02 | CLASHAVOON KNOCKRAHA | bar: Week 16 Tu 19 to Week 16 Th 21
TO-22-DND-T122-01 | DARNDALE T122 | bar: Week 16 Tu 19 to Week 16 Th 21
TO-22-KPG-TB-2-01 | KILPADDOGE TARBERT 2 | bar: Week 16 Tu 19 to Week 16 Th 21
Report covers outages commencing/returning/spanning the period: 11/04/2022 - 24/04/2022
Outages commencing/returning in Week 16
OUTAGE ID | PLANT | Week 15 Mo 11: Week 15; Week 16 Mo 18: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-22-AA GIS-110SA1-2CB-01 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 16 Tu 19 to Week 16 Fr 22
TO-22-220 kV A3 @ CDU-02 | CORDUFF 220 kV A3 | bar: Week 16 Tu 19 to Week 16 Fr 22
TO-22-220 kV B3 @ CDU-02 | CORDUFF 220 kV B3 | bar: Week 16 Tu 19 to Week 16 Fr 22
TO-22-KPG-110K4-01 | KILPADDOGE 110K4 | bar: Week 16 Tu 19 to Week 16 Fr 22
TO-22-AA GIS-LIM-1-01 | ARDNACRUSHA GIS LIMERICK | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-BK-CBR-1-04 | BELLACORICK CASTLEBAR | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-220 kV A2 @ GOR-02 | GORMAN 220 kV A2 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-220 kV B2 @ GOR-02 | GORMAN 220 kV B2 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-KLN-LIM-2-01 | KILLONAN LIMERICK 2 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-KPG-KNR-1-110-01 | KILPADDOGE KNOCKANURE 110 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-LIM-110SA1-01 | LIMERICK 110SA1 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-LIM-110SA2-01 | LIMERICK 110SA2 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-LIM-RAT-1-01 | LIMERICK RATHKEALE | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-LIM-T142-01 | LIMERICK T142 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-220 kV A2 @ MAY-01 | MAYNOOTH 220 kV A2 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-MAY-WOO-1-03 | MAYNOOTH WOODLAND | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-TB-T2102-01 | TARBERT T2102 | bar: Week 16 Tu 19 to Week 16 Mo 25
TO-22-ARK-220K1-2-02 | ARKLOW 220K1-2 | bar: Su 10 to Week 16 Tu 19
TO-22-ARK-220K1-2-01 | bar: Su 10 to Week 16 Tu 19
TO-22-ARK-CKM GIS-1-01 | ARKLOW CARRICKMINES GIS | bar: Su 10 to Week 16 Tu 19
TO-22-ARK-LWD-1-02 | ARKLOW LODGEWOOD | bar: Su 10 to Week 16 Tu 19
TO-22-ARK-T2101-01 | ARKLOW T2101 | bar: Su 10 to Week 16 Tu 19
TO-22-ARK-T2102-01 | ARKLOW T2102 | bar: Su 10 to Week 16 Tu 19
TO-22-220 kV A1 @ CKM GIS-02 | CARRICKMINES GIS 220 kV A1 | bar: Su 10 to Week 16 Tu 19
TO-22-220 kV A2 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A2 | bar: Su 10 to Week 16 Tu 19
TO-22-CKM GIS-220SA1-2CB-01 | CARRICKMINES GIS 220SA1-2CB | bar: Su 10 to Week 16 Tu 19
TO-22-CBT-220K2-01 | CASTLEBAGOT 220K2 | bar: Week 16 We 20
TO-22-CDK-LWD-1-01 | CASTLEDOCKRELL LODGEWOOD | bar: Week 16 We 20
TO-22-CDK-T121-01 | CASTLEDOCKRELL T121 | bar: Week 16 We 20
TO-22-CDU-MUL-1-02 | CORDUFF MULLINGAR | bar: Week 16 We 20
TO-22-DND-110SB1-2CB-01 | DARNDALE 110SB1-2CB | bar: Week 16 We 20
TO-22-110 kV A1/A2 @ KLS-01 | KELLIS 110 kV A1/A2 | bar: Week 16 We 20
TO-22-110 kV B1/B2 @ KLS-01 | KELLIS 110 kV B1/B2 | bar: Week 16 We 20
TO-22-KIN-T101-02 | KINNEGAD T101 | bar: Week 16 We 20
TO-22-LWD-110SA1-02 | LODGEWOOD 110SA1 | bar: Week 16 We 20
TO-22-LWD-110SA2-01 | LODGEWOOD 110SA2 | bar: Week 16 We 20
TO-22-LOU-T2103-03 | LOUTH T2103 | bar: Week 16 We 20
TO-22-MUL-110SA1-2CB-02 | MULLINGAR 110SA1-2CB | bar: Week 16 We 20
TO-22-MUL-CAP2-02 | MULLINGAR CAP2 | bar: Week 16 We 20
TO-22-MUL-T102-01 | MULLINGAR T102 | bar: Week 16 We 20
TO-22-MUL-T142-01 | MULLINGAR T142 | bar: Week 16 We 20
TO-22-ARK-T101-01 | ARKLOW T101 | bar: Week 16 We 20 to Week 16 Th 21
TO-22-DRM-LET-1-01 | DRUMKEEN LETTERKENNY | bar: Week 16 We 20 to Week 16 Th 21
TO-22-LWD-220K1-2-01 | LODGEWOOD 220K1-2 | bar: Week 16 We 20 to Week 16 Th 21
TO-22-MLC-T121-02 | MOUNTLUCAS T121 | bar: Week 16 We 20 to Week 16 Th 21
TO-22-220 kV B2 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B2 | bar: Week 16 We 20 to Week 16 Mo 25
TO-22-220 kV B4 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B4 | bar: Week 16 We 20 to Week 16 Mo 25
TO-22-CKM GIS-220SB2-4CB-01 | CARRICKMINES GIS 220SB2-4CB | bar: Week 16 We 20 to Week 16 Mo 25
TO-22-LWD-T2102-01 | LODGEWOOD T2102 | bar: Week 16 We 20 to Week 16 Mo 25
TO-22-CBT-220SB1-2CB-01 | CASTLEBAGOT 220SB1-2CB | bar: Week 16 Th 21
TO-22-ARK-LWD-1-01 | ARKLOW LODGEWOOD | bar: Su 10 to Week 16 Th 21
TO-22-GOR-LOU-1-01 | GORMAN LOUTH | bar: Week 16 Fr 22 to Week 16 Mo 25
Outages spanning Weeks 15-16
OUTAGE ID | PLANT | Week 15 Mo 11: Week 15; Week 16 Mo 18: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-22-AA GIS-T104-01 | ARDNACRUSHA GIS T104
TO-22-BIN-T142-01 | BINBANE T142
TO-22-CLG-T122-01 | CLOGHRAN T122
Report covers outages commencing/returning/spanning the period: 11/04/2022 - 24/04/2022
Outages spanning Weeks 15-16
OUTAGE ID | PLANT | Week 15 Mo 11: Week 15; Week 16 Mo 18: Week 16
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-22-CDU-PLA-1-01 | CORDUFF PLATIN
TO-22-DRU-CAP2-02 | DRUMLINE CAP2
TO-22-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN
TO-22-220 kV A1/A2 @ FIN-01 | FINGLAS 220 kV A1/A2
TO-22-FIN-220K1-06 | FINGLAS 220K1
TO-22-FIN-220K2-01 | FINGLAS 220K2
TO-22-FIN-MCD-1-01 | FINGLAS McDERMOTT
TO-22-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-LIS-LOU-1-01 | LISDRUM LOUTH
TO-22-LIS-LOU-1-03
TO-22-110 kV A2 @ LOU-02 | LOUTH 110 kV A2
TO-22-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-22-MAY-WOO-1-02 | MAYNOOTH WOODLAND
TO-22-MAY-WOO-1-12
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-RYB GIS-T133-02 | RYEBROOK GIS T133
TO-22-SOM-T142-01 | SOMERSET T142
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1
TO-22-TB-T101-02 | TARBERT T101
TO-22-TB-T102-02 | TARBERT T102
TO-22-TB-T2004-03 | TARBERT T2004
TO-22-WOO-T4201-01 | WOODLAND T4201
TO-22-WOO-T4201-05