## Wks 1 - 2
Report covers outages commencing/returning/spanning the period: 02/01/2023 - 15/01/2023
Outages commencing/returning in Week 1
OUTAGE ID | PLANT |  | Week 1 | [6 empty] | Week 2
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-23-AA GIS-110K3-01 | ARDNACRUSHA GIS 110K3 | bar: Week 1 Tu 3
TO-23-BYH-110K1-01 | BALLYNAHULLA 110K1 | bar: Week 1 We 4
TO-23-BYH-220SA1-2CB-01 | BALLYNAHULLA 220SA1-2CB | bar: Week 1 Th 5
TO-23-110 kV A1/A2 @ KLS-01 | KELLIS 110 kV A1/A2 | bar: Week 1 Th 5
TO-23-110 kV B1/B2 @ KLS-01 | KELLIS 110 kV B1/B2 | bar: Week 1 Th 5
TO-23-BYH-220SB1-2CB-01 | BALLYNAHULLA 220SB1-2CB | bar: Week 1 Fr 6
Outages commencing/returning in Week 2
OUTAGE ID | PLANT | Week 1 Mo 2: Week 1; Week 2 Mo 9: Week 2
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-23-CSH-GAL-2-04 | CASHLA GALWAY 2 | bar: Week 2 Mo 9 to Week 2 Tu 10
TO-23-110 kV A4 @ KPG-01 | KILPADDOGE 110 kV A4 | bar: Week 2 Mo 9 to Week 2 We 11
TO-23-110 kV B4 @ KPG-01 | KILPADDOGE 110 kV B4 | bar: Week 2 Mo 9 to Week 2 We 11
TO-23-KPG-110K4-01 | KILPADDOGE 110K4 | bar: Week 2 Mo 9 to Week 2 We 11
TO-23-220 kV A3 @ KPG-01 | KILPADDOGE 220 kV A3 | bar: Week 2 Mo 9 to Week 2 We 11
TO-23-220 kV B3 @ KPG-01 | KILPADDOGE 220 kV B3 | bar: Week 2 Mo 9 to Week 2 We 11
TO-23-KPG-220K3-01 | KILPADDOGE 220K3 | bar: Week 2 Mo 9 to Week 2 We 11
TO-23-220 kV A2 @ GI GIS-01 | GREAT ISLAND GIS 220 kV A2 | bar: Week 2 Mo 9 to Week 2 Fr 13
TO-23-220 kV B2 @ GI GIS-01 | GREAT ISLAND GIS 220 kV B2 | bar: Week 2 Mo 9 to Week 2 Fr 13
TO-23-GI GIS-220K2-01 | GREAT ISLAND GIS 220K2 | bar: Week 2 Mo 9 to Week 2 Fr 13
TO-23-RYB GIS-T109-02 | RYEBROOK GIS T109 | bar: Week 2 Mo 9 to Week 2 Mo 16
TO-23-110 kV A1/A2 @ BVK-01 | BALLYVOUSKILL 110 kV A1/A2 | bar: Week 2 Tu 10
TO-23-110 kV B1/B2 @ BVK-01 | BALLYVOUSKILL 110 kV B1/B2 | bar: Week 2 Tu 10
TO-23-220 kV A1/A2 @ BVK-01 | BALLYVOUSKILL 220 kV A1/A2 | bar: Week 2 Tu 10
TO-23-220 kV B1/B2 @ BVK-01 | BALLYVOUSKILL 220 kV B1/B2 | bar: Week 2 Tu 10
TO-23-KLS-220K1-2-01 | KELLIS 220K1-2 | bar: Week 2 Tu 10
TO-23-KYT-WOO-1-03 | KELLYSTOWN WOODLAND | bar: Week 2 Tu 10 to Week 2 We 11
TO-23-WOO-T4202-03 | WOODLAND T4202 | bar: Week 2 Tu 10 to Week 2 We 11
TO-23-CDU-220K1-3-01 | CORDUFF 220K1-3 | bar: Week 2 We 11
TO-23-MP GIS-400SA1-3CB-01 | MONEYPOINT GIS 400SA1-3CB | bar: Week 2 We 11
TO-23-110 kV A1/A2 @ CF-01 | CATHALEENS FALL 110 kV A1/A2 | bar: Week 2 Th 12
TO-23-110 kV B1/B2 @ CF-01 | CATHALEENS FALL 110 kV B1/B2 | bar: Week 2 Th 12
TO-23-KIR-T131-01 | KILCUMBER T131 | bar: Week 2 Th 12
TO-23-KYT-MAY-1-01 | KELLYSTOWN MAYNOOTH | bar: Week 2 Th 12 to Week 2 Fr 13
TO-23-110 kV A1 @ KPG-01 | KILPADDOGE 110 kV A1 | bar: Week 2 Th 12 to Week 2 Mo 16
TO-23-110 kV A1/A2 @ KPG-01 | KILPADDOGE 110 kV A1/A2 | bar: Week 2 Th 12 to Week 2 Mo 16
TO-23-110 kV A2 @ KPG-01 | KILPADDOGE 110 kV A2 | bar: Week 2 Th 12 to Week 2 Mo 16
TO-23-KPG-110SA1-2CB-01 | KILPADDOGE 110SA1-2CB | bar: Week 2 Th 12 to Week 2 Mo 16
Outages spanning Weeks 1-2
OUTAGE ID | PLANT | Week 1 Mo 2: Week 1; Week 2 Mo 9: Week 2
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT

## Wks 3 - 4
Report covers outages commencing/returning/spanning the period: 16/01/2023 - 29/01/2023
Outages commencing/returning in Week 3
OUTAGE ID | PLANT |  | Week 3 | [6 empty] | Week 4
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-23-KLN-T2103-01 | KILLONAN T2103 | bar: Week 3 Mo 16 to Week 3 We 18
TO-23-GLN-T133-01 | GALLANSTOWN T133 | bar: Week 3 Mo 16 to Week 3 Fr 20
TO-23-MID-WHI-1-01 | MIDLETON WHITEGATE | bar: Week 3 Mo 16 to Week 3 Fr 20
TO-23-110 kV A1 @ KPG-01 | KILPADDOGE 110 kV A1 | bar: Su 15 to Week 3 Mo 16
TO-23-110 kV A1/A2 @ KPG-01 | KILPADDOGE 110 kV A1/A2 | bar: Su 15 to Week 3 Mo 16
TO-23-110 kV A2 @ KPG-01 | KILPADDOGE 110 kV A2 | bar: Su 15 to Week 3 Mo 16
TO-23-KPG-110SA1-2CB-01 | KILPADDOGE 110SA1-2CB | bar: Su 15 to Week 3 Mo 16
TO-23-110 kV A1/A2 @ GI-01 | GREAT ISLAND 110 kV A1/A2 | bar: Week 3 Tu 17
TO-23-110 kV B1/B2 @ GI-01 | GREAT ISLAND 110 kV B1/B2 | bar: Week 3 Tu 17
TO-23-220 kV A1/A2 @ GI GIS-01 | GREAT ISLAND GIS 220 kV A1/A2 | bar: Week 3 Tu 17
TO-23-220 kV B1/B2 @ GI GIS-01 | GREAT ISLAND GIS 220 kV B1/B2 | bar: Week 3 Tu 17
TO-23-PB-R223-4-02 | POOLBEG R223-4 | bar: Week 3 Tu 17
TO-23-RYB GIS-110K4-01 | RYEBROOK GIS 110K4 | bar: Week 3 Tu 17
TO-23-110 kV A1/A3 @ KPG-01 | KILPADDOGE 110 kV A1/A3 | bar: Week 3 Tu 17 to Week 3 Th 19
TO-23-220 kV A1 @ KPG-01 | KILPADDOGE 220 kV A1 | bar: Week 3 Tu 17 to Week 3 Th 19
TO-23-220 kV A1/A2 @ KPG-01 | KILPADDOGE 220 kV A1/A2 | bar: Week 3 Tu 17 to Week 3 Th 19
TO-23-220 kV A2 @ KPG-01 | KILPADDOGE 220 kV A2 | bar: Week 3 Tu 17 to Week 3 Th 19
TO-23-KPG-220SA1-2CB-01 | KILPADDOGE 220SA1-2CB | bar: Week 3 Tu 17 to Week 3 Th 19
TO-23-RYB GIS-110SB1-3CB-01 | RYEBROOK GIS 110SB1-3CB | bar: Week 3 We 18
TO-23-110 kV A1/A2 @ ARV-01 | ARVA 110 kV A1/A2 | bar: Week 3 Th 19
TO-23-110 kV B1/B2 @ ARV-01 | ARVA 110 kV B1/B2 | bar: Week 3 Th 19
TO-23-220 kV A2 @ KYT-03 | KELLYSTOWN 220 kV A2 | bar: Week 3 Th 19 to Week 4 Mo 23
TO-23-KYT-220K2-02 | KELLYSTOWN 220K2 | bar: Week 3 Th 19 to Week 4 Mo 23
TO-23-KYT-220SA1-2CB-04 | KELLYSTOWN 220SA1-2CB | bar: Week 3 Th 19 to Week 4 Mo 23
TO-23-110 kV A1 @ KPG-02 | KILPADDOGE 110 kV A1 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-110 kV A2 @ KPG-02 | KILPADDOGE 110 kV A2 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-110 kV A2/A4 @ KPG-01 | KILPADDOGE 110 kV A2/A4 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-110 kV A3 @ KPG-01 | KILPADDOGE 110 kV A3 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-110 kV A4 @ KPG-02 | KILPADDOGE 110 kV A4 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-KPG-110SA1-3CB-01 | KILPADDOGE 110SA1-3CB | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-KPG-110SA2-4CB-01 | KILPADDOGE 110SA2-4CB | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-220 kV A1 @ KPG-02 | KILPADDOGE 220 kV A1 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-220 kV A1/A3 @ KPG-01 | KILPADDOGE 220 kV A1/A3 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-220 kV A3 @ KPG-02 | KILPADDOGE 220 kV A3 | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-KPG-220SA1-3CB-01 | KILPADDOGE 220SA1-3CB | bar: Week 3 Fr 20 to Week 4 Tu 24
TO-23-GAL-T102-01 | GALWAY T102 | bar: Week 3 Fr 20 to Week 4 Mo 30
TO-23-GAL-T142-02 | GALWAY T142 | bar: Week 3 Fr 20 to Week 4 Mo 30
Outages commencing/returning in Week 4
OUTAGE ID | PLANT | Week 3 Mo 16: Week 3; Week 4 Mo 23: Week 4
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-23-220 kV A1 @ GI GIS-01 | GREAT ISLAND GIS 220 kV A1 | bar: Week 4 Mo 23 to Week 4 Fr 27
TO-23-220 kV B1 @ GI GIS-01 | GREAT ISLAND GIS 220 kV B1 | bar: Week 4 Mo 23 to Week 4 Fr 27
TO-23-GI GIS-220K1-01 | GREAT ISLAND GIS 220K1 | bar: Week 4 Mo 23 to Week 4 Fr 27
TO-23-110 kV A1/A2/A3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A1/A2/A3 | bar: Week 4 Tu 24
TO-23-110 kV B1/B2/B3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B1/B2/B3 | bar: Week 4 Tu 24
TO-23-INC-MAY-2-02 | INCHICORE MAYNOOTH 2 | bar: Week 4 Tu 24 to Week 4 We 25
TO-23-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2 | bar: Week 4 Tu 24 to Week 4 We 25
TO-23-MAY-220K1-2-02 | MAYNOOTH 220K1-2 | bar: Week 4 Tu 24 to Week 4 We 25
TO-23-220 kV A2 @ KYT-01 | KELLYSTOWN 220 kV A2 | bar: Week 4 Tu 24 to Week 4 Fr 27
TO-23-220 kV B2 @ KYT-01 | KELLYSTOWN 220 kV B2 | bar: Week 4 Tu 24 to Week 4 Fr 27
TO-23-KYT-220K2-01 | KELLYSTOWN 220K2 | bar: Week 4 Tu 24 to Week 4 Fr 27
TO-23-KYT-220SA1-2CB-01 | KELLYSTOWN 220SA1-2CB | bar: Week 4 Tu 24 to Week 4 Fr 27
TO-23-KYT-220SB1-2CB-01 | KELLYSTOWN 220SB1-2CB | bar: Week 4 Tu 24 to Week 4 Fr 27
TO-23-220 kV A2 @ KPG-02 | KILPADDOGE 220 kV A2 | bar: Week 4 We 25 to Week 4 Fr 27
TO-23-220 kV A2/A4 @ KPG-01 | KILPADDOGE 220 kV A2/A4 | bar: Week 4 We 25 to Week 4 Fr 27
TO-23-220 kV A4 @ KPG-01 | KILPADDOGE 220 kV A4 | bar: Week 4 We 25 to Week 4 Fr 27
TO-23-KPG-220SA2-4CB-01 | KILPADDOGE 220SA2-4CB | bar: Week 4 We 25 to Week 4 Fr 27
TO-23-110 kV A1/A2/A4 @ KNR-01 | KNOCKANURE 110 kV A1/A2/A4 | bar: Week 4 Th 26
Report covers outages commencing/returning/spanning the period: 16/01/2023 - 29/01/2023
Outages commencing/returning in Week 4
OUTAGE ID | PLANT | Week 3 Mo 16: Week 3; Week 4 Mo 23: Week 4
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-23-110 kV B1/B2/B4 @ KNR-01 | KNOCKANURE 110 kV B1/B2/B4 | bar: Week 4 Th 26
TO-23-220 kV A1/A2 @ KNR-01 | KNOCKANURE 220 kV A1/A2 | bar: Week 4 Th 26
TO-23-220 kV B1/B2 @ KNR-01 | KNOCKANURE 220 kV B1/B2 | bar: Week 4 Th 26
Outages spanning Weeks 3-4
OUTAGE ID | PLANT | Week 3 Mo 16: Week 3; Week 4 Mo 23: Week 4
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-RYB GIS-T109-02 | RYEBROOK GIS T109

## Wk 5
Report covers outages commencing/returning/spanning the period: 30/01/2023 - 05/02/2023
Outages commencing/returning in Week 5
OUTAGE ID | PLANT |  | Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-220 kV A2 @ KYT-02 | KELLYSTOWN 220 kV A2 | bar: Week 5 Mo 30 to Week 5 Tu 31
TO-23-KYT-220K2-03 | KELLYSTOWN 220K2 | bar: Week 5 Mo 30 to Week 5 Tu 31
TO-23-KYT-220SA1-2CB-02 | KELLYSTOWN 220SA1-2CB | bar: Week 5 Mo 30 to Week 5 Tu 31
TO-23-KYT-WOO-1-01 | KELLYSTOWN WOODLAND | bar: Week 5 Mo 30 to Week 5 Tu 31
TO-23-GAL-T102-01 | GALWAY T102 | bar: Su 29 to Week 5 Th 2
Outages spanning Week 5
OUTAGE ID | PLANT | Week 5 Mo 30: Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
TO-23-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-23-FIN GIS-110K6-01 | FINGLAS GIS 110K6
TO-23-GAL-T142-02 | GALWAY T142
TO-23-INC-220K1-2-01 | INCHICORE 220K1-2
TO-23-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-23-MUL-CAP2-01 | MULLINGAR CAP2
TO-23-PB-R2002-02 | POOLBEG R2002
TO-23-PRO-TB-1-04 | PROSPECT TARBERT
TO-23-RYB GIS-T109-02 | RYEBROOK GIS T109